## Risk Register
ID | Risk | NIST Function | Likelihood | Impact | Overall | Existing / Planned Control | Control Type | Owner | Monitoring Indicator | Residual Risk | Status
R-01 | Hallucination / incorrect loan, fee or account information | Map / Measure / Manage | Medium | Medium | Medium | Curated accuracy benchmark; sampled conversation review; human escalation | Preventive + Detective + Corrective | AI Risk Owner | Factual error rate; disputed responses | Medium | Conditional
R-02 | Prompt injection manipulates the agent outside intended scope | Map / Measure / Manage | Medium | Medium | Medium | Prompt-injection red-team testing; input/output filtering; anomaly detection | Preventive + Detective | Security / AI Risk Owner | Injection alerts; red-team findings | Medium | Conditional
R-03 | PII leakage through session handling or excessive log access | Map / Measure / Manage | Low | High | Medium | Data minimization; need-to-know log access; PII-handling review | Preventive + Detective | Privacy / Security | PII incidents; access exceptions | Low–Medium | Conditional
R-04 | Users or staff over-rely on unscoped AI output | Map / Manage | Medium | Medium | Medium | Clear scope; human escalation; customer dissatisfaction routing | Preventive + Corrective | Business Owner | Escalation rate; complaints | Medium | Conditional
R-05 | Knowledge/model drift after product or policy changes | Map / Measure / Manage | Medium | Low | Low–Medium | Knowledge-base change control; recurring accuracy review | Preventive + Detective | Business Owner / Technology | Stale-content findings; accuracy trend | Low | Conditional
R-06 | Unauthorized transaction initiation if scope controls fail | Map / Measure / Manage | Low* | Severe | Medium | System-level read-only permissions; no transaction capability; scope testing | Preventive | Technology / Security | Permission-test failures | Low–Medium | Critical control

## Scoring Methodology
Field | Method
Likelihood | Qualitative judgment: Low / Medium / High
Impact | Qualitative judgment: Low / Medium / High; Severe used where stated in the final assessment
Overall | Portfolio judgment based on the assessment's qualitative combination; not a statistical probability
Residual Risk | Risk remaining after planned controls; controls reduce or contain risk rather than guaranteeing elimination
Important | The ratings are illustrative and should be recalibrated against real monitoring data in a real deployment.